# 2026-04-20 MPP OI Review — Internal Status Summary

Document: MPP-MES-STATUS-2026-04-22 Version: 1.1 Date: 2026-04-22 Prepared By: Blue Ridge Automation Audience: Internal Blue Ridge status meeting

Summary of changes from the 2026-04-20 MPP customer review, framed in terms of complexity impact and new work required. Companion to Meeting_Notes/2026-04-20_OI_Review.md (raw notes) and MPP_MES_Open_Issues_Register.md (v2.4 register).

## Revision History

| Version | Date | Author | Change Summary |
| --- | --- | --- | --- |
| 1.0 | 2026-04-22 | Blue Ridge Automation | Initial internal status summary following 2026-04-20 MPP OI Review meeting. Captures scope shifts, new items, phase progress, blockers, and risks. |
| 1.1 | 2026-04-22 | Blue Ridge Automation | Added “Additional discovered gaps” section following 2026-04-22 review of reference/MPP_Current_MES_screenshots.docx (36 screenshots). Enumerates 9 concrete design additions + 7 discovery items now logged as OI-15 through OI-30 in the Open Issues Register v2.5. |
| 1.2 | 2026-04-22 | Blue Ridge Automation | OI-11 entry updated: resolved via 1-line BOM (not a new Parts.ItemTransform table as the v1.1 row suggested). See Open Issues Register v2.6 for the reversal. |

## Headline

The 2026-04-20 customer review closed 2 items, revised 6, reopened 2 with addenda, added 4 new items, and promoted Tool Management from a single data-model attribute to a first-class subsystem. Net effect: 4 of 7 planned refactor phases are already done; the remaining work is scoped but front-loaded with one large SQL migration.

## Scope shifts ranked by complexity impact

### Large — Tool Management (OI-10 → Phase B spec, Phase G SQL)

- Before: Tool was a single LocationAttribute carrying a die identifier.

- After: New Tools schema (10 tables): Tool, ToolCavity, ToolAssignment (check-in/out), ToolAttribute, two status code tables, DieRank + DieRankCompatibility matrix, polymorphic ToolType.

- Why it matters: Ripples into OI-05 (merge rules reference rank compatibility), OI-07 (Maintenance WOs target a Tool), and the sublot workflow (per-cavity lots). Design spec already approved (commit 47ce9c7). SQL delivery is Phase G — est. ~35 procs + ~60 tests in a new migration 0010_phase9_tools_and_workorder.sql.

### Large — Operator identity rewrite (OI-06, Phase C)

- Before: Clock number + PIN shop-floor login with session-sticky elevation.

- After: Initials-only presence (no login), per-action AD re-prompt for elevated actions, dedicated vs shared terminal modes, 30-min idle re-confirm.

- Status: Already delivered (commit dbeac08). Schema cleanup (drop ClockNumber/PinHash) deferred to Phase G — migration drops both columns in the same file that creates Tools.

- Still open: Tom owes final elevated-action list.

### Medium — Three Work Order types (OI-07)

- Before: Single “WO” concept, MVP-lite invisible-to-operators.

- After: Demand / Maintenance / Recipe types. Demand is as-designed. Maintenance WO targets a ToolId (schema hook only, flow is FUTURE). Recipe hidden from operator.

- Impact: Minor schema change (Workorder.WorkOrderType code table + nullable ToolId). Bigger unknown is Maintenance lifecycle — Ben owes scope before Phase G can close.

### Medium — LOT merge rules (OI-05)

- Before: Business rules undefined.

- After: Post-sort only, same part, cross-die allowed only when ranks are compatible (with supervisor AD override), FIFO-by-cavity on machining, quality-status gating with no override.

- Impact: Merge validation procedure couples to Tools.DieRankCompatibility. MPP Quality still owes the full rank compatibility matrix — the table is seeded empty with reject-with-override as the fallback.

### Medium — Vision conflict / CRT workflow (OI-04)

- Before: Proposed auto-LOT-hold + supervisor override.

- After: Line-stop (not LOT hold). 10-consecutive-fail escalation with configurable threshold. Branch by failure type (wrong-part → leader flag; wrong-orientation → no escalation). New Lots.Lot.CrtActive flag for 200% inspect workflow.

- Impact: Requires a new escalation-state model but no invasive schema churn. Delivered as part of Phase D FDS rewrite.

### Small — Sublots (OI-09 addenda)

- Before: “One part at a time” — assumed simple.

- After: Per-cavity concurrent sublots from a parent lot, each with its own label carrying a parent reference.

- Impact: Existing Lots.Lot.ParentLotId adjacency list already supports this. Work is primarily label design + sublot-aware scan flows.

### Small — Terminal modes (OI-08 addenda)

- Before: Shared terminals with machine-scan-first.

- After: 80% dedicated / 20% shared via TerminalMode LocationAttribute; terminal locked to machine context; tablets for casting (mobile design input); Honda RFID flagged FUTURE.

- Impact: Minor FDS §2.5 addenda, no schema changes beyond attribute seed rows.

### Resolved / simplification — Shift runtime (OI-03)

- Before: Debate over how to capture lunch/break/OT adjustments on paper forms.

- After: MES captures events + durations only, never minute adjustments. Runtime derives from events. Shift schedule imports from MPP’s spreadsheet.

- Impact: Simpler than the original proposal. Phase 8 SQL already supports this.

## Four new items surfaced (previously unknown)

| OI | Priority | Complexity | Notes |
| --- | --- | --- | --- |
| OI-11 — Part rename Casting → Trim | MEDIUM | ✅ Resolved — no new schema | Modelled as 1-line BOM (trim part has cast part as sole component at QtyPer=1); existing ConsumptionEvent + LotGenealogy carries it. Initial v1.8 draft added a Parts.ItemTransform table but it was fully redundant with ConsumptionEvent — reverted 2026-04-22. |
| OI-12 — Lineside inventory caps | MEDIUM | Small — MaxParts on ContainerConfig + LinesideLimit LocationAttribute | Prevents scan-in gaming |
| OI-13 — BOM source system | HIGH | Medium — one-shot export from Flexware (IP .919) at cutover | Need export format from MPP IT |
| OI-14 — Admin remove-item | LOW | Small — already in FDS-04-007 elevated actions list | Design + proc only |

## Work done vs. work remaining (the 7-phase refactor plan)

| Phase | Scope | Status |
| --- | --- | --- |
| C — Security rewrite | OI-06: initials-only identity, AD elevation | Done (dbeac08) |
| A — OI register refresh | v2.4, rebuilt as sectioned markdown | Done (1e68426) |
| B — Tool Mgmt design spec | 10-table Tools schema, data-model v1.7 | Done (47ce9c7 + b3893d5) |
| D — Remaining FDS rewrites | §§2.5, 5.4, 5.5, 6.10, 9.4, 10.3 | Done (b3893d5) |
| E — Cross-cutting OI-11..14 | Part rename, lineside caps, BOM import, admin delete | Queued (design + doc only) |
| F — Regenerate derived artifacts | ERD, Word docs, SUMMARY index refresh | Queued (housekeeping) |
| G — SQL Phase 9 | 0010_phase9_tools_and_workorder.sql + ~35 procs + ~60 tests | Queued (largest remaining chunk) |

Takeaway for the status meeting: the documentation tier is ~80% through the refactor; the remaining implementation weight sits in Phase G (Tools + WorkOrderType SQL) which is a self-contained, multi-session effort.

## External blockers (what we can’t close without)

- Tom (MPP security) — final elevated-action validation pass (blocks final Phase C closeout on the FDS-04-007 list).

- Ben (MPP maintenance SME) — Maintenance WO engine scope & lifecycle (blocks Phase G Maintenance flow beyond the schema hook).

- MPP Quality — full die-rank compatibility matrix (Phase G seeds table empty with reject-with-override until received).

- MPP IT — Flexware .919 BOM export format (blocks OI-13 bulk-load design).

- MPP Production Control — shift schedule spreadsheet template (helps Phase E but not blocking).

## Risk callouts

- Phase G is the largest single piece of new SQL work since Phase 5. Tool schema + WorkOrderType migration + procs + tests is a multi-session effort; don’t underestimate. The design is locked, so it’s execution risk, not design risk.

- OI-11 (Casting → Trim rename) was not anticipated — genealogy bridge design is net-new architectural work, not a mechanical change.

- Die rank matrix lead time — if MPP Quality slips on delivering the matrix, cross-die merges fall back to “always reject with supervisor override” at go-live, which may be too restrictive for the floor.

## Additional discovered gaps (2026-04-22 legacy screenshot review)

Source: reference/MPP_Current_MES_screenshots.docx — 36 screenshots of the Flexware Madison MES covering Landing, Orders, Configuration (Materials, Site, Workstations, Security), runtime Workstations (Casting, Tumbling, Sort), and Create flows. Reviewed against current FDS v0.9 + Data Model v1.7.

Headline: the big-ticket items (Orders, Site, Security, Casting create flow, Move Lot, Holds, Sort scan) are already covered in our design, often more rigorously (three-state BOM lifecycle, initials-based identity, Tools schema). 16 net-new items surfaced — 9 concrete additions + 7 discovery items — now logged as OI-15 through OI-30 in the Open Issues Register v2.5.

### Concrete design additions (9 items)

| OI | Priority | Gap | Proposed direction |
| --- | --- | --- | --- |
| OI-15 | HIGH | Global Track screen — non-workstation path to look up any LOT / serial / container and view genealogy | Dedicated Perspective home-tile screen. Honda traceability is the core mission. |
| OI-16 | MEDIUM | WO auto-finish-on-target semantics (camera count / scale weight target) | Extend Workorder.ProductionEvent_Record and §6.10 to fire WO-close when cumulative count / weight reaches WO target. |
| OI-17 | MEDIUM | Tray-divisibility validation on WO close (target must be evenly divisible by tray quantity) | Validate at WO Create/Edit and Close in Workorder.WorkOrder_*. |
| OI-18 | MEDIUM | Parts.ItemLocation missing Min / Max / Default quantity + Consumption Point | Add four columns; feeds runtime Allocations grid. Phase E design + Phase G SQL. |
| OI-19 | LOW effort / HIGH compliance | Parts.Item.CountryOfOrigin | Add NVARCHAR(2) NULL (ISO 3166-1 alpha-2). Honda genealogy output. |
| OI-20 | LOW | Scrap source enum (Inventory vs Location) — two distinct scrap paths | Add ScrapSource code table + ScrapSourceId on Workorder.ProductionEvent. |
| OI-21 | MEDIUM | Partial start / partial complete at a workstation (start N now, complete M later) | Verify ProductionEvent_Record supports decoupled Start and Complete; extend if not. |
| OI-22 | MEDIUM | Dedicated Hold Management screen (top-level tile in legacy) | Perspective screen listing active holds with supervisor-elevated place / release. |
| OI-23 | LOW | Lot derived TotalInProcess / InventoryAvailable exposed in header | Document derivation in §5; decide view-vs-materialized. |

### Discovery items to confirm with MPP (7 items)

| OI | Priority | Item | Why flag it |
| --- | --- | --- | --- |
| OI-24 | MEDIUM | Automation top-level tile contents unknown | Likely OPC / interface management. Need walk-through before ruling in or out. |
| OI-25 | LOW | Notifications configuration module | Email / alert rules. Probably out-of-MVP but confirm so it isn’t a regression surprise. |
| OI-26 | LOW | Per-workstation dashboard scripting hook (Edit Script per save button) | Ignition Perspective handles scripting at project level — one-to-one port not idiomatic. Verify nothing load-bearing exists. |
| OI-27 | LOW | Material Supply part BIT purpose | Unknown. Ask MPP before ignoring. |
| OI-28 | MEDIUM | Work Cell “Require override for cast parts” flag | Ties to OI-04 line-stop / vision flow at cell granularity. Confirm retention. |
| OI-29 | LOW | Workstation Category grouping orthogonal to Area/Line | UI convenience (e.g., Sort / Shipping / Tumbling as peers of lines). Our ISA-95 hierarchy may already cover it. |
| OI-30 | MEDIUM | Reports tile full contents not enumerated | UJ-19 lists 4 PD reports but full menu unwalked. Avoid scope surprise at go-live. |

### Impact on plan

- Phase E (cross-cutting design) was already queued for OI-11..14; it now also carries OI-15..23 (concrete design). No new phase needed.

- Phase G (SQL migration 0010_phase9_tools_and_workorder.sql) grows modestly — OI-18 (ItemLocation columns), OI-19 (CountryOfOrigin), OI-20 (ScrapSource) are small additive schema changes that can ride along. No additional migration file required.

- Discovery items (OI-24..30) produce one consolidated question list to bring to the next MPP review session. Three of them (OI-24, OI-28, OI-30) could reshape scope if answers come back unexpected — worth flagging on the agenda.

## References

- Meeting_Notes/2026-04-20_OI_Review.md — raw meeting notes (2026-04-20)

- MPP_MES_Open_Issues_Register.md — v2.5 register (OI-15..30 added 2026-04-22)

- reference/MPP_Current_MES_screenshots.docx — 36 legacy MES screenshots reviewed 2026-04-22

- memory/project_mpp_oi_refactor.md — 7-phase execution plan

- docs/superpowers/specs/2026-04-21-tool-management-design.md — Phase B design spec v0.2

- MPP_MES_FDS.md v0.9 — rewritten §§2.5, 4, 5.4, 5.5, 6.10, 9.4, 10.3

- MPP_MES_DATA_MODEL.md v1.7 — Tools schema + WorkOrderType