## Sheet1
# | Area | Sub-Area | Current Status | FRS Proposal | Section | Notes
1 | Implementation | Production / Asset Model | Currently supported | Included
2 | Implementation | Data Migration | NA | Not included conditionally | 3.6.0 | 80 Hours New Quote for MD, ProdDB
3 | Production | Receiving | Not supported | Pass-through (not raw / dunnage) Parts Included | 2.1.1
4 | Production | Work Orders | Not supported | Included conditionally | 3.1.5, 3.10.0
5 | Production | Scheduling | Not supported | Not Included | 3.12.1 | Future
6 | Production | Inventory / WIP | Currently supported | Included
7 | Production | Lot Control | Currently supported | Included
8 | Quality | Inspections | Currently supported | Included
9 | Quality | Sampling | Not supported | Included conditionally | 2.1.9, 3.16.0
10 | Quality | No-go part Inventory Tracking | Not supported | Not Included
11 | Quality | Holds | Currently supported | Included and Expanded | 2.1.8, 3.16.10
12 | Quality | Leak Tests | Not supported | Not Included |  | Future
13 | Quality | Torque Checks | Not supported | Not Included |  | Future
14 | Quality | Nonconformance Mgmt, Failure Analysis | Not supported | Not Included
15 | Performance | Production Data Acquisition | Currently Supported | Included and Expanded | 3.5.4 | Rejects Report, Die Shot Report, Downtime Report, Production Report
16 | Performance | OEE | Not supported | Not Included
17 | Performance | Downtime | Not supported | Included | 3.15.0
18 | Performance | KPIs | Not supported | Not Included
19 | Traceability | Produced Parts Tracking | Currently supported | Included
20 | Traceability | Pass-through Parts Tracking | Not supported | Included | 2.1.12, 5.6.4 | Future
21 | Traceability | Raw Material Tracking | Not supported | Not Included |  | Future
22 | Traceability | Serialization | Currently supported on two lines | Included | 2.1.10 | Expanded Scope
23 | Traceability | Part Replacement | Not supported | Included
24 | Traceability | Shipping Holds | Currently supported | Included
25 | Maintenance | Work Orders | Not supported | Not Included
26 | Maintenance | Tool Life | Not supported | Included | 5.6.6
27 | Integrations | ERP | Macola, Not supported | Not Included |  | Future
28 | Integrations | SCADA | None, Not supported | Not Included
29 | Integrations | Quality | Intelex, Not supported | Not Included | 5.6.7 | Future
30 | Integrations | Shipping | AIM, Currently supported | Included
31 | Integrations | Maintenance | None, Not supported | Not Included
32 | Integrations | Production DB | Not supported | Not included conditionally | 3.14.0, 5.6.6
33 | Integrations | PLC Connections | Currently Supported OPCUA for Cameras, Scales, Printers, Scanners, Laser? (no machines) | Included
34 | SCADA | Process Data Dashboards | Not supported | Not Included |  | Future
35 | SCADA | Historization / Trending | Unknown | Included | 3.4.10, 5.5.1
36 | SCADA | Process Reporting | Not supported | Not Included | 3.5.14 | Expanded Scope
37 | SCADA | Alarming | Unknown | Included conditionally | 3.4.8