# MPP MES — Seeding Registry

Document: FDS-MPP-MES-SEED-001 Version: 1.0 — Initial draft Date: 2026-04-27 Prepared By: Blue Ridge Automation Prepared For: Madison Precision Products, Inc. (Madison, IN)

This registry tracks every seed-data item the MES requires from sources external to Blue Ridge (MPP IT, MPP Quality, MPP Engineering, Honda AIM, vendor exports). Internal code-table seeds baked into migrations are NOT tracked here — those ship with the SQL.

Seeding items are NOT blockers for design or SQL build work. Schemas, procs, and screens proceed in parallel; this registry exists so we collect the data alongside the build and load it during the cutover phase. An item is only a “blocker” if a downstream design decision genuinely requires its content (rare — flagged explicitly per item below).

## Revision History

| Version | Date | Author | Change Summary |
| --- | --- | --- | --- |
| 1.0 | 2026-04-27 | Blue Ridge Automation | Initial registry. Catalogues 11 external-source seed items extracted from CLAUDE.md “MPP-owed” + “MPP data loads” sections. Establishes the registry as the single source of truth for seed-data tracking, removing seed items from the “blocking specific downstream work” framing in CLAUDE.md. |

## Status Legend

| Badge | Meaning |
| --- | --- |
| ⬜ Owed | File / list / decision not yet received from external source. |
| 🟡 Received | Delivered to Blue Ridge; not yet loaded into dev. |
| ✅ Loaded (Dev) | Loaded into dev SQL DB; queryable; tests passing where applicable. |
| 🔵 Verified (Cutover) | Loaded into production-equivalent + validated by the responsible MPP stakeholder. |

## Summary

| ID | Item | Target | Status | Owner | Blocking? |
| --- | --- | --- | --- | --- | --- |
| S-01 | Plant equipment master | Location.Location (Cell-tier) | 🟡 Received | MPP Eng. for tier mapping | No |
| S-02 | Downtime reason codes | Oee.DowntimeReasonCode | 🟡 Received | MPP Eng. for DC/MS/TS→Area mapping | No |
| S-03 | Defect codes | Quality.DefectCode | 🟡 Received | MPP Quality for Area mapping | No |
| S-04 | OPC tag catalog | Ignition OPC config (not SQL) | 🟡 Received | MPP Eng. for endpoint validation | No |
| S-05 | Parts master list | Parts.Item | ⬜ Owed | MPP IT (export from Macola/Flexware) | No |
| S-06 | Flexware BOM export | Parts.Bom + Parts.BomLine | ⬜ Owed | MPP IT (OI-13 — two-pull) | No |
| S-07 | Die rank list | Tools.DieRank | ⬜ Owed | MPP Quality | No |
| S-08 | Die rank compatibility matrix | Tools.DieRankCompatibility | ⬜ Owed | MPP Quality | Yes — gates cross-die merges (FDS-05-027) without supervisor override |
| S-09 | Label-type seed validation | Lots.LabelTypeCode (already seeded with Blue Ridge guesses) | ⬜ Owed | MPP Shipping | No |
| S-10 | Identifier sequence baselines | Lots.IdentifierSequence.LastValue | ⬜ Owed | MPP IT (snapshot at cutover) | Cutover-only — not blocking dev |
| S-11 | AIM pool config tuning | Lots.AimPoolConfig (defaults already seeded 50/30/20/10) | 🟡 Received (defaults) | MPP for post-deploy tuning | No |

Counts: 6 ⬜ Owed · 5 🟡 Received · 0 ✅ Loaded (Dev) · 0 🔵 Verified (Cutover)

True blockers: 1 (S-08 die rank compatibility — and even this has a supervisor-override workaround until populated).

## Per-Item Detail

### S-01 — Plant Equipment Master (Machines)

Status: 🟡 Received Source: reference/seed_data/machines.csv (209 rows extracted from FRS Appendix B by Blue Ridge) Target: Location.Location rows (Cell tier) + Location.LocationAttribute values for tonnage / cycle time / etc. Owner: MPP Engineering — for tier mapping (DeptCode → AreaLocationId) and verification that the 2024 FRS extract still reflects today’s plant. Blocking: No — schema, procs, and screens proceed without this. Plant model exercises against 12 dev sample rows in sql/seeds/seed_locations.sql.

File format: CSV — columns: MachId, MachNo, MachDesc, Tonnage, DeptDesc, MinPerShift, RefCycleTime, DeptCode, ProcId, ProcDesc. Full column docs in reference/seed_data/README.md.

Mapping owed from MPP Engineering: - DeptCode (DC, MS, TR, AS) → AreaLocationId (the actual Location.Id of each Area row). - Confirmation that the 209-row FRS list is current — flag any decommissioned / new equipment since 2024. - Validation that each row’s LocationTypeDefinition (DieCastMachine vs CNCMachine vs TrimPress vs AssemblyStation, derived from ProcDesc) is correct.

Loading procedure: Bulk-load proc not yet written. Follows the Oee.DowntimeReasonCode_BulkLoadFromSeed JSON-fed pattern (S-02) — caller supplies a @DeptCodeToAreaIdMap JSON; proc inserts Location.Location rows + Location.LocationAttribute values per the FRS columns; deterministic Code generation {DeptCode}-{MachNo}.

Acceptance criteria: 1. All 209 rows (or MPP-revised count) load without error. 2. Each row’s parent AreaLocationId matches the MPP-supplied mapping. 3. LocationAttribute rows for Tonnage, RefCycleTime, MinPerShift are present where the CSV has non-empty values. 4. Location.LocationTypeDefinitionId matches the CSV’s ProcDesc.

### S-02 — Downtime Reason Codes

Status: 🟡 Received Source: reference/seed_data/downtime_reason_codes.csv (353 rows extracted from FRS Appendix D — DC=86, MS=239, TS=25) Target: Oee.DowntimeReasonCode Owner: MPP Engineering — for DC/MS/TS → Area mapping and per-row DowntimeReasonType backfill where the CSV has missing TypeDesc. Blocking: No — Oee.DowntimeEvent capture works against an empty DowntimeReasonCode set; reasons can be assigned later. OEE reporting requires this loaded before go-live.

File format: CSV — columns: DeptCode, ReasonId, ReasonDesc, TypeDesc, IsExcused. Full column docs in reference/seed_data/README.md.

Mapping owed from MPP Engineering: - DeptCode (DC, MS, TS) → AreaLocationId (3 area Location IDs). - Backfill DowntimeReasonType for any row where CSV TypeDesc is missing — engineering-level review can be done in dev via _Update calls on rows with NULL DowntimeReasonTypeId.

Loading procedure: Oee.DowntimeReasonCode_BulkLoadFromSeed @ReasonsJson, @DcAreaId, @MsAreaId, @TsAreaId, @AppUserId — built and tested in Phase 8. JSON-fed bulk load; deterministic Code generation {DeptCode}-{NNNN} (zero-padded ReasonId).

Acceptance criteria: 1. All 353 rows load (or MPP-revised count) without uniqueness violations on Code. 2. Rows with missing TypeDesc load with DowntimeReasonTypeId = NULL; engineering backfills via _Update before go-live. 3. The MPP-supplied DC/MS/TS → Area IDs match the actual Area rows in Location.Location.

### S-03 — Defect Codes

Status: 🟡 Received Source: reference/seed_data/defect_codes.csv (153 rows extracted from FRS Appendix E) Target: Quality.DefectCode Owner: MPP Quality — for AreaLocationId mapping and confirmation that the FRS extract is current. Blocking: No — non-conformance capture works against an empty DefectCode set.

File format: CSV — columns: DefectId, DefectCode, DefectDesc, AreaCode, IsExcused (or similar — see reference/seed_data/README.md).

Mapping owed from MPP Quality: - AreaCode → AreaLocationId. - Confirmation that the 2024 FRS list still reflects today’s defect catalogue — flag adds / removes.

Loading procedure: Bulk-load proc not yet written. Follows the DowntimeReasonCode_BulkLoadFromSeed JSON pattern.

Acceptance criteria: 1. All 153 rows (or MPP-revised count) load. 2. AreaLocationId mapping matches the MPP-supplied Area IDs.

### S-04 — OPC Tag Catalog

Status: 🟡 Received Source: reference/seed_data/opc_tags.csv (161 rows extracted from FRS Appendix C) Target: Ignition OPC server configuration (NOT a SQL table). OmniServer for scales; TOPServer / SWToolbox for PLCs; Cognex for vision. Owner: MPP Engineering — for endpoint IP / port validation and live-tag verification. Blocking: No — Ignition OPC config can be assembled as Phase 7 progresses.

File format: CSV — columns: ServerName, ServerPid, Direction, AccessPath, OpcItemId. Full column docs in reference/seed_data/README.md.

Validation owed from MPP Engineering: - Endpoint IP / port for each OPC server (cross-reference with reference/NewInput/5GO-AP4 IPAddresses.xlsx). - Live verification that each tag is reachable and behaves per the FRS (read/write direction, value type, rate).

Loading procedure: Manual import into Ignition Designer at Arc 2 Phase 7 (OPC configuration phase).

Acceptance criteria: 1. Every OpcItemId resolves and reads/writes per the FRS spec on the live PLC/scale.

### S-05 — Parts Master List

Status: ⬜ Owed Source: MPP IT export from Macola ERP and/or Flexware MES current parts table. Target: Parts.Item Owner: MPP IT — for the export. Blocking: No — Parts.Item_Create / _Update procs work against an empty table; sample parts can be seeded for dev. Production cutover needs the full list before go-live.

File format owed from MPP IT: CSV or XLSX with at minimum: PartNumber, Description, MacolaPartNumber (optional), DefaultUomCode, UnitWeight (optional), WeightUomCode (optional), CountryOfOrigin (ISO 3166-1 alpha-2), MaxLotSize / PartsPerBasket (per-basket capacity), MaxParts (per-Location cap, optional), ItemType (Raw/Component/SubAssembly/FinishedGood). Format conversation with MPP IT pending.

Mapping owed from MPP: - ItemType per row — likely derivable from MPP ERP categories. - CountryOfOrigin per row — Honda compliance field (FDS-03-001).

Loading procedure: Bulk-load proc not yet written; format depends on what MPP IT exports.

Acceptance criteria: 1. Every part on MPP’s master list loads as an Item row with non-empty PartNumber (UNIQUE), valid UomId FK, and correct ItemType FK. 2. CountryOfOrigin populated where MPP has the data.

### S-06 — Flexware BOM Export (OI-13)

Status: ⬜ Owed Source: MPP IT export from the live Flexware MES at IP .919. Target: Parts.Bom + Parts.BomLine Owner: MPP IT — for the export tooling and execution. Blocking: No — Bom / BomLine schema and procs are built (Phase 6); empty-table operation is fine for non-BOM-driven flows. BOM-driven flows (Trim 1-line BOM consumption per FDS-05-033, Assembly material verification per FDS-06-011) need this loaded before go-live.

Two-pull plan (per OI-13): 1. NOW — one-shot pull for dev validation: load into dev DB, verify schema fit, exercise the Bom_GetActiveForItem flow on a representative sample. Catches export-format issues before cutover. 2. At cutover — fresh pull on cutover day to capture any BOM changes between dev validation and go-live.

File format owed from MPP IT: TBD — depends on what Flexware exports. Likely two CSVs (bom_header.csv + bom_line.csv) or a JSON tree. Format conversation pending.

Loading procedure: Bulk-load proc not yet written; written after MPP IT confirms export format.

Acceptance criteria: 1. Every Flexware BOM round-trips to Parts.Bom + Parts.BomLine without error. 2. Sample-part Bom_GetActiveForItem returns the expected component list. 3. Versioning: imported BOMs land as Published rows (not Draft) — they’re already in active use at MPP.

Coupling: Requires S-05 (Parts master) to be loaded first — BomLine.ChildItemId FKs into Item.

### S-07 — Die Rank List

Status: ⬜ Owed Source: MPP Quality. Target: Tools.DieRank (currently empty seed) Owner: MPP Quality — for the canonical rank list. Blocking: No — Tools.Tool rows can be created with DieRankId = NULL; rank assignment can be backfilled. Cross-die merges that require rank checks (S-08) are the only flow that needs this loaded.

Format owed: Simple list of rank codes + descriptions (e.g., A, B, C with descriptions).

Loading procedure: Manual Tools.DieRank_Create calls (~10 rows expected).

Acceptance criteria: 1. All MPP-defined ranks present as Tools.DieRank rows.

### S-08 — Die Rank Compatibility Matrix

Status: ⬜ Owed — TRUE BLOCKER (with supervisor-override workaround) Source: MPP Quality. Target: Tools.DieRankCompatibility (currently empty seed) Owner: MPP Quality — owes the full pairwise compatibility matrix. Blocking: Yes — Lots.Lot_Merge rejects cross-die merges until at least the relevant rank pair exists in the matrix. Supervisor AD elevation (FDS-04-007) provides an override path until populated, so the workaround is real but adds operator friction.

Format owed: Pairwise list (RankA_Code, RankB_Code, CanMix BIT). Or symmetric matrix in xlsx.

Loading procedure: Manual Tools.DieRankCompatibility_Create calls per pair (or a small bulk-load proc if matrix is wide).

Acceptance criteria: 1. Every pair MPP Quality identifies as compatible has a row with CanMix = 1. 2. Default behavior for unlisted pairs: reject merge (proc enforces this).

Depends on: S-07 (DieRank list).

### S-09 — Label Type Code Validation

Status: ⬜ Owed (validation only — values already seeded by Blue Ridge) Source: Blue Ridge proposed values from Honda shipping conventions: Primary, Container, Master, Void. Loaded via Phase 3 migration 0004_phase3_reference_lookups.sql. Target: Lots.LabelTypeCode (4 rows already in dev DB) Owner: MPP Shipping — for confirmation / corrections. Blocking: No — labels print against whatever’s seeded; if values change, an update migration is trivial.

Validation owed from MPP Shipping: - Confirm the four seeded values match Honda’s terminology and operational vocabulary. - Flag any additional types (e.g., Repack, Reprint) that should be seeded.

Loading procedure: Already loaded. Updates land as a small versioned migration if values change.

### S-10 — Identifier Sequence Baselines (Cutover Snapshot)

Status: ⬜ Owed (cutover-only — not blocking dev) Source: Snapshot of Flexware live counter values for Lot (~1,710,932 baseline) and SerializedItem (~2,492 baseline) on cutover day. Target: Lots.IdentifierSequence.LastValue for the two seeded rows (Lot MESL{0:D7}, SerializedItem MESI{0:D7}). Owner: MPP IT — for the snapshot reading. Blocking: No — dev DB seeds with LastValue = 0; the cutover migration overwrites with Flexware values to ensure ID continuity.

Snapshot owed from MPP IT: Two integer reads from Flexware on cutover day (delivered as a 2-row CSV or just two numbers in an email).

Loading procedure: Cutover migration: UPDATE Lots.IdentifierSequence SET LastValue = @MppLotValue WHERE Code = 'Lot'; + same for SerializedItem.

Acceptance criteria: 1. First MES-issued Lot LotName = MESL{Flexware_LastValue + 1:D7} — no overlap, no gap. 2. Same for SerializedItem.

### S-11 — AIM Pool Configuration Tuning

Status: 🟡 Received (defaults seeded by Blue Ridge) Source: Defaults shipped with Arc 2 Phase 7 migration: TargetBufferDepth = 50, TopupThreshold = 30, AlarmWarningDepth = 20, AlarmCriticalDepth = 10. Target: Lots.AimPoolConfig (single-row table; one seeded row) Owner: MPP — for post-deploy tuning based on observed peak container throughput vs AIM responsiveness. Blocking: No.

Tuning input owed from MPP (post-deploy): - Observed peak containers/hour across all dedicated Assembly terminals combined. - Observed AIM GetNextNumber response time (mean + p99). - Operational tolerance for AIM-outage windows (how long should production survive an AIM outage on the buffer alone).

Loading procedure: Configuration Tool exposes Lots.AimPoolConfig_Update @TargetBufferDepth, @TopupThreshold, @AlarmWarningDepth, @AlarmCriticalDepth (Admin-elevated per FDS-04-007).

## Adding a New Seeding Item

When a new external-data dependency surfaces: 1. Add a row to the Summary table with the next S-NN ID. 2. Add a per-item detail section below. 3. If the item is a true blocker (rare), flag it in both the summary table’s “Blocking?” column and in CLAUDE.md’s “Decision blockers” list. 4. Update the Revision History.

## Marking an Item Loaded

When MPP delivers data and it lands in dev: 1. Update the item’s status badge to ✅ Loaded (Dev) in the summary table and the per-item section. 2. Capture the actual row count loaded vs the originally-quoted count. 3. Update the Revision History.

When the item is verified in a cutover-equivalent environment (post-Phase 0 customer validation workshop or equivalent): 1. Update the badge to 🔵 Verified (Cutover). 2. Capture the responsible MPP stakeholder + date of validation. 3. Update the Revision History.